|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| No | Month  of  start | | Month of  end | Title | Description of activates, components, means | Expected output/deliverables | Partner |
| 1 | 01/2018 | | 12/2020 | Carpathian Convention Implementation Committee (CCIC) | **2-3 meetings** and continuous online consultations.  Preparation of comprehensive information and documentation for the 6th Meeting of the Conference of the Parties to the Carpathian Convention – COP 6, guidance and overview of the implementation and work conducted under thematic Working Groups, review of MoUs, agreements and other relevant initiatives under the Convention | * documentation on sectoral issues, integrated reports, strategies/ strategic action plans/protocols for priority issues, * WGs Terms of Reference, * meeting reports and recommendations | EURAC |
| 2 | 01/2018 | | 12/2020 | Working Groups/workshops under CCIC | Backgrounds documentation, meetings of the Working Groups experts and continuous online consultation | Background documentation, meetings, reports, recommendations |  |
|  | | | | a) Working Group on Conservation and Sustainable Use of Biological and Landscape Diversity (WG Biodiversity) | **2-3 meetings** and continuous online consultations.   * elaboration of the Carpathian joint action plan for population based large carnivore conservation and management; * finalization of the Carpathian Red Lists, * analysation of the Biodiversity Protocol Implementation Reports; * Guidance of TransGREEN project on ecological connectivity and Green Infrastructure * support in project development * proposal for new priorities | * Carpathian joint action plan for population based large carnivore conservation and management elaborated * Carpathian Red Lists finalised * Biodiversity Protocol Implementation Reports submitted regularly and analysed * support given to the development of the follow up projects and activities related to biological and landscape diversity, landscapes, ecological connectivity and green infrastructure | UNEP  EURAC,  UNEP/GRID Warsaw,  WWF -DCP  CNAP  ALPARC  CWI |
| b) Steering Committee of the Carpathian Network of Protected Area (CNPA) | **1 -2 meetings** or online consultation, where appropriate jointly with the WG Biodiversity | * support in the development of one flagship activity with CNPA management unit * Cooperation with Alpine and Danube Networks of Protected Areas | CNPA Unit, WWF-DCP  EURAC  CWI / SNC  ALPARC |
| c) Working Group on Spatial Development | **1-2 meetings** or online consultations.   * information-sharing and coordination of projects developed for application to the European, and those approved under the Danube transnational programme (TransGREEN) * possible joint meeting(s) with other WGs, especially with WG Biodiversity * connection with landscapes, Green Infrastructure, ecological connectivity | * support in development and implementation of transnational projects aiming at implementing the Carpathian Convention | EU  EURAC  WWF-DCP  UNEP/GRID Warsaw |
| d) Working Group on Sustainable Agriculture and Rural Development | **2-3 meetings** and continuous online consultations.   * implementation of the Protocol on Sustainable Agriculture and Rural Development (SARD Protocol) * support in elaboration of the Strategic Action Plan to the SRAD Protocol (SAP-SARD Protocol) * support in elaboration of the Report Format for implementation of the SARD Protocol * support in development in possible projects * promotion of sustainable agricultural practices in the Carpathian region. * possible joint meeting(s) with other WGs | * inputs for proposals for follow up activities and projects with the view of implementing the provisions of the SARD Protocol * SAP-SARD Protocol elaborated * Report Format elaborated | EURAC  FAO |
| e) Working Group on Sustainable Forest Management | **2-3 meetings** and continuous online consultations.   * elaboration of the Carpathian Convention Inventory of the Virgin Forest * support in developing definition and indicators for forest naturalness, * implementation of the Partnership Agreement with the European Environment Agency * elaboration of the Report Format for implementation of the Forest Protocol * possible meeting(s) with other WGs | * inputs for proposals for follow up activities and projects with the view of implementing the provisions of the Forest Protocol and its Strategic Action Plan * Carpathian Inventory/Map of the Virgin Forest elaborated * Harmonizing definition and indicators for forest naturalness * Report Format for implementation of the Forest Protocol elaborated | EEA,  Forest Europe,  EURAC,  WWF-DCP,  UNEP and GRIDs |
| f) Working Group on Sustainable Industry, Energy, Transport and infrastructure | 2-3 meetings / workshops and continuous online consultations.   * further implementation of the Protocol on Sustainable Transport * support in development of Strategic Action Plan to the Protocol on Sustainable Transport (SAP – Transport Protocol) * Report Format for implementation of the Transport Protocol * Involvement in a possible workshop on sustainable energy in mountain areas of the Danube region * support in implementation of the TRANSGREEN project * possible joint meeting(s) with other WGs.   Connection with green infrastructure, landscapes and ecological connectivity | * inputs for proposals for follow up activities and projects with the view of implementing the provisions of the Protocol on Sustainable Transport * SAP – Transport Protocol developed * Report Format for implementation of the Transport Protocol elaborated * Workshop organized | EURAC,  EUSDR  UNEP/GRID Warsaw,  UNEP/GRID Arendal  WWF-DCP |
|  | | | | g) Working Group on Sustainable Tourism | **2 meetings** and continuous online consultations.   * guidelines and coordination of the implementation of the Protocol on Sustainable Tourism * Report Format for implementation of the Tourism Protocol elaborated * possible joint meeting(s) with other WGs | * inputs to the follow up activities and project with the view of further implementation of the Protocol on Sustainable Tourism and its Strategy * Report Format for implementation of the Tourism Protocol elaborated | EURAC  ETE  UNWTO |
|  | | | | h) Working Group on Cultural Heritage and Traditional Knowledge | **2-3 meetings** and continuous online consultations.   * elaboration of a draft Protocol on the Cultural Heritage and Traditional Knowledge * support in elaboration of the Strategic Action Plan to the Protocol * possible joint meeting(s) with other WGs. | * Protocol on Cultural Heritage and Traditional Knowledge developed * Strategic Action Plan to the Protocol elaborated | EURAC  UNEP/GRID Warsaw |
|  | | | | i) Working Group on Adaptation to Climate Change | **2-3 meetings** and continuous online consultations.   * coordination of the implementation of the Strategic Agenda on adaptation to climate change * support in project development * follow up to regional adaptation policy assessment * possible joint meeting(s) with other WGs | * good practices for adaptation, mitigation, DRR identified and disseminated | Tisza Group  Alpine Convention  EURAC  Szent István University,  EEA |
| 3 | | **2020** | | 6th Meeting of the Conference of the Parties to the Carpathian Convention (COP6) |  |  | All partners |