|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No | Monthofstart | Month ofend | Title | Description of activates, components, means | Expected output/deliverables | Partner |
| 1 | 01/2018 | 12/2020 | Carpathian Convention Implementation Committee (CCIC) | **2-3 meetings** and continuous online consultations.Preparation of comprehensive information and documentation for the 6th Meeting of the Conference of the Parties to the Carpathian Convention – COP 6, guidance and overview of the implementation and work conducted under thematic Working Groups, review of MoUs, agreements and other relevant initiatives under the Convention  | * documentation on sectoral issues, integrated reports, strategies/ strategic action plans/protocols for priority issues,
* WGs Terms of Reference,
* meeting reports and recommendations
 | EURAC |
| 2 | 01/2018 | 12/2020 | Working Groups/workshops under CCIC  | Backgrounds documentation, meetings of the Working Groups experts and continuous online consultation  | Background documentation, meetings, reports, recommendations |  |
|  | a) Working Group on Conservation and Sustainable Use of Biological and Landscape Diversity (WG Biodiversity) | **2-3 meetings** and continuous online consultations. * elaboration of the Carpathian joint action plan for population based large carnivore conservation and management;
* finalization of the Carpathian Red Lists,
* analysation of the Biodiversity Protocol Implementation Reports;
* Guidance of TransGREEN project on ecological connectivity and Green Infrastructure
* support in project development
* proposal for new priorities
 | * Carpathian joint action plan for population based large carnivore conservation and management elaborated
* Carpathian Red Lists finalised
* Biodiversity Protocol Implementation Reports submitted regularly and analysed
* support given to the development of the follow up projects and activities related to biological and landscape diversity, landscapes, ecological connectivity and green infrastructure
 | UNEPEURAC,UNEP/GRID Warsaw,WWF -DCPCNAPALPARCCWI |
| b) Steering Committee of the Carpathian Network of Protected Area (CNPA)  | **1 -2 meetings** or online consultation, where appropriate jointly with the WG Biodiversity  | * support in the development of one flagship activity with CNPA management unit
* Cooperation with Alpine and Danube Networks of Protected Areas
 | CNPA Unit, WWF-DCPEURACCWI / SNCALPARC |
| c) Working Group on Spatial Development  | **1-2 meetings** or online consultations. * information-sharing and coordination of projects developed for application to the European, and those approved under the Danube transnational programme (TransGREEN)
* possible joint meeting(s) with other WGs, especially with WG Biodiversity
* connection with landscapes, Green Infrastructure, ecological connectivity
 | * support in development and implementation of transnational projects aiming at implementing the Carpathian Convention
 | EUEURAC WWF-DCPUNEP/GRID Warsaw |
| d) Working Group on Sustainable Agriculture and Rural Development  | **2-3 meetings** and continuous online consultations.* implementation of the Protocol on Sustainable Agriculture and Rural Development (SARD Protocol)
* support in elaboration of the Strategic Action Plan to the SRAD Protocol (SAP-SARD Protocol)
* support in elaboration of the Report Format for implementation of the SARD Protocol
* support in development in possible projects
* promotion of sustainable agricultural practices in the Carpathian region.
* possible joint meeting(s) with other WGs
 | * inputs for proposals for follow up activities and projects with the view of implementing the provisions of the SARD Protocol
* SAP-SARD Protocol elaborated
* Report Format elaborated
 | EURACFAO |
| e) Working Group on Sustainable Forest Management  | **2-3 meetings** and continuous online consultations.* elaboration of the Carpathian Convention Inventory of the Virgin Forest
* support in developing definition and indicators for forest naturalness,
* implementation of the Partnership Agreement with the European Environment Agency
* elaboration of the Report Format for implementation of the Forest Protocol
* possible meeting(s) with other WGs
 | * inputs for proposals for follow up activities and projects with the view of implementing the provisions of the Forest Protocol and its Strategic Action Plan
* Carpathian Inventory/Map of the Virgin Forest elaborated
* Harmonizing definition and indicators for forest naturalness
* Report Format for implementation of the Forest Protocol elaborated
 | EEA,Forest Europe,EURAC,WWF-DCP,UNEP and GRIDs |
| f) Working Group on Sustainable Industry, Energy, Transport and infrastructure  | 2-3 meetings / workshops and continuous online consultations.* further implementation of the Protocol on Sustainable Transport
* support in development of Strategic Action Plan to the Protocol on Sustainable Transport (SAP – Transport Protocol)
* Report Format for implementation of the Transport Protocol
* Involvement in a possible workshop on sustainable energy in mountain areas of the Danube region
* support in implementation of the TRANSGREEN project
* possible joint meeting(s) with other WGs.

Connection with green infrastructure, landscapes and ecological connectivity | * inputs for proposals for follow up activities and projects with the view of implementing the provisions of the Protocol on Sustainable Transport
* SAP – Transport Protocol developed
* Report Format for implementation of the Transport Protocol elaborated
* Workshop organized
 | EURAC,EUSDRUNEP/GRID Warsaw,UNEP/GRID ArendalWWF-DCP |
|  | g) Working Group on Sustainable Tourism  | **2 meetings** and continuous online consultations.* guidelines and coordination of the implementation of the Protocol on Sustainable Tourism
* Report Format for implementation of the Tourism Protocol elaborated
* possible joint meeting(s) with other WGs
 | * inputs to the follow up activities and project with the view of further implementation of the Protocol on Sustainable Tourism and its Strategy
* Report Format for implementation of the Tourism Protocol elaborated
 | EURACETEUNWTO |
|  | h) Working Group on Cultural Heritage and Traditional Knowledge  | **2-3 meetings** and continuous online consultations.* elaboration of a draft Protocol on the Cultural Heritage and Traditional Knowledge
* support in elaboration of the Strategic Action Plan to the Protocol
* possible joint meeting(s) with other WGs.
 | * Protocol on Cultural Heritage and Traditional Knowledge developed
* Strategic Action Plan to the Protocol elaborated
 | EURACUNEP/GRID Warsaw |
|  | i) Working Group on Adaptation to Climate Change  | **2-3 meetings** and continuous online consultations.* coordination of the implementation of the Strategic Agenda on adaptation to climate change
* support in project development
* follow up to regional adaptation policy assessment
* possible joint meeting(s) with other WGs
 | * good practices for adaptation, mitigation, DRR identified and disseminated
 | Tisza GroupAlpine Convention EURAC Szent István University,EEA |
| 3 | **2020** | 6th Meeting of the Conference of the Parties to the Carpathian Convention (COP6) |  |  | All partners  |